## P
UniqueID | Sr. No | Product Name | Order Processing Date | Promised Delivery Date | Quantity Required | Components | Operation | Process Type | Machine Number | Run Time (min/1000) | Cycle Time (seconds) | Setup time (seconds) | Ready Time | Start Time | End Time | Wait Time | Status | Time Diff | SetupTimeCheck
1 | 1 | Product 1 | 2024-08-21 09:00 | 2024-08-28 17:00 | 9000 | C1 | Op1 | In House | M1 | 10 | 1.08 | 10000 | 2024-08-21 09:00
2 | 1 | Product 1 | 2024-08-21 09:00 | 2024-08-28 17:00 | 9000 | C2 | Op2 | Outsource | OutSrc | 1440 |  | 0 | 2024-08-21 09:00
3 | 1 | Product 1 | 2024-08-21 09:00 | 2024-08-28 17:00 | 9000 | C3 | Op3 | In House | M2 | 20 | 7.2 | 10000 | 2024-08-21 09:00
4 | 1 | Product 1 | 2024-08-21 09:00 | 2024-08-28 17:00 | 9000 | C4 | Op4 | In House | M1 | 30 | 1.08 | 10000 | 2024-08-21 09:00
5 | 1 | Product 1 | 2024-08-21 09:00 | 2024-08-28 17:00 | 9000 | C5 | Op5 | In House | M3 | 15 | 7.2 | 10000 | 2024-08-21 09:00
6 | 1 | Product 1 | 2024-08-21 09:00 | 2024-08-28 17:00 | 9000 | C6 | Op5 | In House | M3 | 14 | 7.2 | 10000 | 2024-08-21 09:00
7 | 2 | Product 2 | 2024-08-21 09:00 | 2024-08-27 17:00 | 4000 | C1 | Op1 | In House | M1 | 30 | 3 | 0 | 2024-08-21 09:00
8 | 2 | Product 2 | 2024-08-21 09:00 | 2024-08-27 17:00 | 4000 | C2 | Op2 | In House | M2 | 30 | 7.2 | 10000 | 2024-08-21 09:00
9 | 2 | Product 2 | 2024-08-21 09:00 | 2024-08-27 17:00 | 4000 | C3 | Op3 | Outsource | OutSrc | 700 |  | 0 | 2024-08-21 09:00
10 | 3 | Product 3 | 2024-08-21 09:00 | 2024-09-02 17:00 | 15000 | C1 | Op1 | Outsource | OutSrc | 1440 |  | 0 | 2024-08-21 09:00
11 | 3 | Product 3 | 2024-08-21 09:00 | 2024-09-02 17:00 | 15000 | C2 | Op2 | In House | M1 | 30 | 1.08 | 0 | 2024-08-21 09:00
12 | 3 | Product 3 | 2024-08-21 09:00 | 2024-09-02 17:00 | 15000 | C3 | Op3 | In House | M2 | 40 | 7.2 | 10000 | 2024-08-21 09:00
13 | 4 | Product 4 | 2024-08-21 09:00 | 2024-08-29 17:00 | 5000 | C1 | Op1 | Outsource | OutSrc | 750 | 1.08 | 0 | 2024-08-21 09:00
14 | 4 | Product 4 | 2024-08-21 09:00 | 2024-08-29 17:00 | 5000 | C2 | Op2 | In House | M1 | 35 |  | 10000 | 2024-08-21 09:00
15 | 4 | Product 4 | 2024-08-21 09:00 | 2024-08-29 17:00 | 5000 | C3 | Op3 | In House | M2 | 30 | 7.2 | 10000 | 2024-08-21 09:00
16 | 5 | Product 5 | 2024-08-21 09:00 | 2024-08-30 17:00 | 3000 | C1 | Op1 | In House | M1 | 40 | 1.08 | 10000 | 2024-08-21 09:00
17 | 5 | Product 5 | 2024-08-21 09:00 | 2024-08-30 17:00 | 3000 | C2 | Op2 | In House | M2 | 40 | 7.2 | 10000 | 2024-08-21 09:00
18 | 5 | Product 5 | 2024-08-21 09:00 | 2024-08-30 17:00 | 3000 | C3 | Op3 | In House | M2 | 35 | 7.2 | 10000 | 2024-08-21 09:00
20 | 6 | Product 6 | 2024-08-21 09:00 | 2024-08-19 17:00 | 4000 | C1 | Op1 | In House | M1 | 30 | 7.2 | 10000 | 2024-08-21 09:00
21 | 6 | Product 6 | 2024-08-21 09:00 | 2024-08-19 17:00 | 4000 | C2 | Op2 | In House | M2 | 30 |  | 10000 | 2024-08-21 09:00
22 | 6 | Product 6 | 2024-08-21 09:00 | 2024-08-19 17:00 | 4000 | C3 | Op3 | In House | M3 | 30 | 1.08 | 10000 | 2024-08-21 09:00

## prodet
UniqueID | Sr. No | Product Name | Order Processing Date | Promised Delivery Date | Quantity Required | Components | Operation | Process Type | Machine Number | Run Time (min/1000) | Cycle Time (seconds) | Setup time (seconds) | Ready Time | Start Time | End Time | Wait Time | Status | Time Diff | SetupTimeCheck | Remaining_days | Time_Needed | Run_time | Final Setup Time | Delay Days | Delay Hours | Time Diff_days | Idle Time
1 | 1 | Product 1 | 2024-08-21 09:00 | 2024-08-28 17:00 | 9000 | C1 | Op1 | In House | M1 | 10 | 1.08 | 10000 | 2024-08-21 09:00 | 2024-08-21 15:01 | 2024-08-21 16:31 | 06:01 | Completed | 01:30 | 0 | -12 | -5760 | 90 | 10000 | 0 | 0 | 0.0625 | 07:30
2 | 1 | Product 1 | 2024-08-21 09:00 | 2024-08-28 17:00 | 9000 | C2 | Op2 | Outsource | OutSrc | 1440 |  | 0 | 2024-08-21 09:00 | 2024-08-21 16:32 | 2024-08-26 16:32 |  | Completed | 00:00 | 1 | -12 | -5760 | 1440 |  |  |  | 5 | 09:00
3 | 1 | Product 1 | 2024-08-21 09:00 | 2024-08-28 17:00 | 9000 | C3 | Op3 | In House | M2 | 20 | 7.2 | 10000 | 2024-08-21 09:00 | 2024-08-26 16:32 | 2024-08-27 11:33 | 07:32 | Completed | 19:00 | 0 | -12 | -5760 | 180 | 10000 | 0 | 0 | 0.79201 | 13:59
4 | 1 | Product 1 | 2024-08-21 09:00 | 2024-08-28 17:00 | 9000 | C4 | Op4 | In House | M1 | 30 | 1.08 | 10000 | 2024-08-21 09:00 | 2024-08-27 11:33 | 2024-08-27 16:03 | 02:33 | Completed | 04:30 | 0 | -12 | -5760 | 270 | 10000 | 0 | 0 | 0.1875 | 04:30
5 | 1 | Product 1 | 2024-08-21 09:00 | 2024-08-28 17:00 | 9000 | C5 | Op5 | In House | M3 | 15 | 7.2 | 10000 | 2024-08-21 09:00 | 2024-08-27 16:04 | 2024-08-28 10:19 | 07:04 | Completed | 18:15 | 0 | -12 | -5760 | 135 | 10000 | 0 | 0 | 0.76042 | 14:45
6 | 1 | Product 1 | 2024-08-21 09:00 | 2024-08-28 17:00 | 9000 | C6 | Op5 | In House | M3 | 14 | 7.2 | 10000 | 2024-08-21 09:00 | 2024-08-28 10:19 | 2024-08-28 12:25 | 01:19 | Completed | 02:06 | 0 | -12 | -5760 | 126 | 10000 | 0 | 0 | 0.0875 | 06:54
7 | 2 | Product 2 | 2024-08-21 09:00 | 2024-08-27 17:00 | 4000 | C1 | Op1 | In House | M1 | 30 | 3 | 0 | 2024-08-21 09:00 | 2024-08-21 16:32 | 2024-08-22 10:32 | 07:32 | Completed | 18:00 | 0 | -13 | -6240 | 120 | 0 | 0 | 0 | 0.75 | 15:00
8 | 2 | Product 2 | 2024-08-21 09:00 | 2024-08-27 17:00 | 4000 | C2 | Op2 | In House | M2 | 30 | 7.2 | 10000 | 2024-08-21 09:00 | 2024-08-22 10:32 | 2024-08-22 12:32 | 01:32 | Completed | 02:00 | 0 | -13 | -6240 | 120 | 10000 | 0 | 0 | 0.083333 | 07:00
9 | 2 | Product 2 | 2024-08-21 09:00 | 2024-08-27 17:00 | 4000 | C3 | Op3 | Outsource | OutSrc | 700 |  | 0 | 2024-08-21 09:00 | 2024-08-22 12:33 | 2024-08-28 12:25 |  | Completed | 23:52 | 1 | -13 | -6240 | 700 |  |  |  | 5.9948 | 09:07
10 | 3 | Product 3 | 2024-08-21 09:00 | 2024-09-02 17:00 | 15000 | C1 | Op1 | Outsource | OutSrc | 1440 |  | 0 | 2024-08-21 09:00 | 2024-08-22 12:33 | 2024-08-29 09:52 |  | Completed | 21:19 | 1 | -7 | -3360 | 1440 |  |  |  | 6.8882 | 11:41
11 | 3 | Product 3 | 2024-08-21 09:00 | 2024-09-02 17:00 | 15000 | C2 | Op2 | In House | M1 | 30 | 1.08 | 0 | 2024-08-21 09:00 | 2024-08-29 09:52 | 2024-08-30 09:23 | 00:52 | Completed | 23:30 | 0 | -7 | -3360 | 450 | 0 | 0 | 0 | 0.97951 | 09:29
12 | 3 | Product 3 | 2024-08-21 09:00 | 2024-09-02 17:00 | 15000 | C3 | Op3 | In House | M2 | 40 | 7.2 | 10000 | 2024-08-21 09:00 | 2024-08-30 09:23 | 2024-09-02 11:24 | 00:23 | Completed | 02:00 | 0 | -7 | -3360 | 600 | 10000 | 0 | 0 | 3.0837 | 06:59
13 | 4 | Product 4 | 2024-08-21 09:00 | 2024-08-29 17:00 | 5000 | C1 | Op1 | Outsource | OutSrc | 750 | 1.08 | 0 | 2024-08-21 09:00 | 2024-08-22 12:33 | 2024-08-28 12:25 |  | Completed | 23:52 | 1 | -11 | -5280 | 750 |  |  |  | 5.9948 | 09:07
14 | 4 | Product 4 | 2024-08-21 09:00 | 2024-08-29 17:00 | 5000 | C2 | Op2 | In House | M1 | 35 |  | 10000 | 2024-08-21 09:00 | 2024-08-28 12:26 | 2024-08-28 15:21 | 03:26 | Completed | 02:55 | 0 | -11 | -5280 | 175 | 10000 | 0 | 0 | 0.12153 | 06:05
15 | 4 | Product 4 | 2024-08-21 09:00 | 2024-08-29 17:00 | 5000 | C3 | Op3 | In House | M2 | 30 | 7.2 | 10000 | 2024-08-21 09:00 | 2024-08-28 15:21 | 2024-08-29 09:52 | 06:21 | Completed | 18:30 | 0 | -11 | -5280 | 150 | 10000 | 0 | 0 | 0.77118 | 14:29
16 | 5 | Product 5 | 2024-08-21 09:00 | 2024-08-30 17:00 | 3000 | C1 | Op1 | In House | M1 | 40 | 1.08 | 10000 | 2024-08-21 09:00 | 2024-08-22 12:33 | 2024-08-22 14:33 | 03:33 | Completed | 02:00 | 0 | -10 | -4800 | 120 | 10000 | 0 | 0 | 0.083333 | 07:00
17 | 5 | Product 5 | 2024-08-21 09:00 | 2024-08-30 17:00 | 3000 | C2 | Op2 | In House | M2 | 40 | 7.2 | 10000 | 2024-08-21 09:00 | 2024-08-22 14:33 | 2024-08-22 16:33 | 05:33 | Completed | 02:00 | 0 | -10 | -4800 | 120 | 10000 | 0 | 0 | 0.083333 | 07:00
18 | 5 | Product 5 | 2024-08-21 09:00 | 2024-08-30 17:00 | 3000 | C3 | Op3 | In House | M2 | 35 | 7.2 | 10000 | 2024-08-21 09:00 | 2024-08-22 16:34 | 2024-08-23 10:19 | 07:34 | Completed | 17:45 | 0 | -10 | -4800 | 105 | 10000 | 0 | 0 | 0.73958 | 15:15
20 | 6 | Product 6 | 2024-08-21 09:00 | 2024-08-19 17:00 | 4000 | C1 | Op1 | In House | M1 | 30 | 7.2 | 10000 | 2024-08-21 09:00 | 2024-08-21 09:00 | 2024-08-21 11:00 | 00:00 | Late | 02:00 | 0 | -21 | -10080 | 120 | 10000 | 2 | 2 | 0.083333 | 07:00
21 | 6 | Product 6 | 2024-08-21 09:00 | 2024-08-19 17:00 | 4000 | C2 | Op2 | In House | M2 | 30 |  | 10000 | 2024-08-21 09:00 | 2024-08-21 11:00 | 2024-08-21 13:00 | 02:00 | Late | 02:00 | 0 | -21 | -10080 | 120 | 10000 | 2 | 4 | 0.083333 | 07:00
22 | 6 | Product 6 | 2024-08-21 09:00 | 2024-08-19 17:00 | 4000 | C3 | Op3 | In House | M3 | 30 | 1.08 | 10000 | 2024-08-21 09:00 | 2024-08-21 13:01 | 2024-08-21 15:01 | 04:01 | Late | 02:00 | 0 | -21 | -10080 | 120 | 10000 | 2 | 6 | 0.083333 | 07:00

## Product Times
Product Name | Total Time | Remaining Time | Time_Needed | Time Left | Date
Product 6 | 360 | 360 | -10080 | -10440 | 10-09-2024
Product 1 | 2241 | 2151 | -5760 | -7911 | 16-09-2024
Product 2 | 940 | 700 | -6240 | -6940 | 11-09-2024
Product 4 | 1075 | 1075 | -5280 | -6355 | 12-09-2024
Product 3 | 2490 | 2490 | -3360 | -5850 | 17-09-2024
Product 5 | 345 | 0 | -4800 | -4800 | 09-09-2024

## Addln
UniqueID | Sr. No | Product Name | Order Processing Date | Promised Delivery Date | Quantity Required | Components | Operation | Process Type | Machine Number | Run Time (min/1000) | Cycle Time (seconds) | Setup time (seconds) | Ready Time | Start Time | End Time | Wait Time | Status | Time Diff

## RunTime
Run_time
12

## Outsource Time
Product | Components | Outsource Time
Product 1 | C2 | 5
Product 2 | C3 | 5
Product 3 | C1 | 5

## Machines
Machines
M1
M2
M3

## Similarity
Machine | Product 1 | Product 2 | Product 3 | Product 4 | Product 5 | Product 6
M1 | 0 | 0 | 0 | 0 | 0 | 0
M2 | 0 | 0 | 0 | 0 | 0 | 0
M3 | 0 | 0 | 0 | 0 | 0 | 0